## Exec Summary
AI4IA Pipeline — Production Readiness Audit
Repository: ai4ia-backend ¦ Branch: release @ 2a2faac ¦ Audit date: 2026-09-15 ¦ Scope: 33,577 LOC backend
VERDICT: NOT READY TO SHIP
Four blockers, two of which are silent-failure modes that will not page anyone: the ingest_jobs queue has no consumer in the deployed path, and the Dockerfile most likely being built reintroduces the yt-dlp bug fixed in 6ed8f77. The test suite is red and CI never runs it, so neither would have been caught.
FINDINGS BY SEVERITY
Severity | Count | Definition
BLOCKER | 4 | Must be fixed before release. Causes data loss, silent failure, or an open security boundary.
HIGH | 14 | Fix before release or accept a named, time-boxed risk with an owner.
MEDIUM | 14 | Fix in the first post-release sprint; degrades reliability or operability.
LOW | 4 | Housekeeping, hygiene, or a recorded correction. No production risk.
TOTAL | 36 | Plus 5 items verified clear — see 'Verified Clear' sheet.
TOP 5 — MUST FIX BEFORE GO-LIVE
Rank | ID | Finding | Why it is ranked here
1 | COR-01 | ingest_jobs queue has no consumer in the deployed path | Every ingest job is accepted, enqueued and never executed. .delay() succeeds so the thread fallback never fires; the job sits at 'queued' forever with no timeout and no alert. Silent.
2 | DEP-01 | Root Dockerfile lacks Node.js, silently breaking every YouTube download | docker/Dockerfile documents that without Node, downloads 'silently fail as not available for every video' — the bug fixed in 6ed8f77. One of the two Dockerfiles ships it broken.
3 | TST-01 | Test suite is red and CI runs no tests at all | 73 failed / 780 passed; a bare pytest will not even collect. No pytest, ruff or image scan in the workflow. There is no gate between a broken commit and production.
4 | SEC-01 | API-key auth fails open; archive/dashboard have no user identity | 'if not settings.api_key: return' — an unset env var silently publishes the full corpus across 11 routes. Startup logs a warning and boots anyway.
5 | COR-02 | No LLM backpressure; OTel unpinned will break the next clean build | Zero concurrency control: ~37% of calls fail under a 16-vs-10 burst because retries are correlated. Separately opentelemetry-api/sdk float against instrumentation pinned at 0.44b0.
OPEN QUESTION — BLOCKS TWO OF THE FIVE ABOVE
Which Dockerfile and which worker command does gaiangroup/access/.github/workflows/python-ai4ia-nexusconnects.yaml@config actually use? This cannot be determined from inside this repository and it gates COR-01 and DEP-01. Note also that the 'release' branch (current HEAD) calls a different workflow from dev/master — python-mobius-graph-operations-release-config.yaml, named for a different service. Confirm that is intentional.
METHOD — Static review of the working tree at release (2a2faac); full 'git log --all -p' secret scan; AST-based timeout audit across backend/app; dependency-constraint resolution against the installed venv; and a full pytest run. No fixes applied — nothing in the working tree was modified.

## Scorecard
Production Readiness Scorecard
One row per audit section. Status reflects the worst unresolved finding in that area.
Area | Status | Blockers / High | Key evidence | Gate
1. Security | AT RISK | 1 BLOCKER, 2 HIGH | core/auth.py:15-19 fails open; archive.py has 10 routes with no user identity; rate_limit.py is per-pod; otel unpinned. | P0
2. Correctness | AT RISK | 1 BLOCKER, 3 HIGH | start.sh:169 consumes one queue; no LLM backpressure anywhere; media registry reads local disk on the API pod. | P0
3. Error handling | PARTIAL | 1 HIGH | All HTTP calls have timeouts (verified by AST pass). Gaps: no resume-from-stage, no dead-letter, FFmpeg relies on stage-level timeouts. | P1
4. Observability | PARTIAL | 3 HIGH | Logging and tracing are genuinely good. No worker health surface, no queue-depth metric, and no alerting at all. | P1
5. Config & Deploy | AT RISK | 1 BLOCKER, 2 HIGH | Two divergent Dockerfiles; CI runs no tests; k8s/ and compose files are stale and actively misleading. | P0
6. Testing | FAILING | 1 BLOCKER, 1 HIGH | Suite does not collect; 73 failures; zero coverage of queue routing, S3 round-trip and job state transitions. | P0
7. Data integrity | AT RISK | 2 HIGH | Silent Chroma/Postgres divergence on partial embedding failure; migrations unordered with a missing 0005; S3 orphans accumulate. | P1

## All Findings
All Findings
Sorted by severity, then section. Use the filter arrows on row 4 to slice by severity, section or effort.
ID | Section | Severity | Finding | File(s) | Line(s) | What's wrong | Why it matters in production | Concrete fix | Effort
SEC-01 | 1. Security | BLOCKER | API-key gate fails open; archive and dashboard carry no user authentication | backend/app/core/auth.py; backend/app/main.py; backend/app/core/settings.py | auth.py:15-19; main.py:394-395; settings.py:416 | require_api_key() returns successfully when settings.api_key is empty: 'if not settings.api_key: return'. Separately, archive_router (10 routes) and dashboard_router (1 route) are mounted with _auth_dep, which is ONLY require_api_key — there is no get_current_user anywhere in archive.py. Every other router either mounts _admin_dep or carries per-endpoint get_current_user. The comparison 'key != settings.api_key' is also non-constant-time. | An unset or mistyped API_KEY in the vCluster secret silently publishes the entire corpus: /archive/videos, /archive/fragments, /archive/search, /archive/semantic-search and video streaming. validate_deployment_env() only appends a warning string and the app boots normally. A missing environment variable should never be the difference between private and public. | 1) Fail closed: raise HTTPException(503) when settings.api_key is unset, and use secrets.compare_digest for the comparison. 2) Add real identity to content routes: _auth_dep = [Depends(require_api_key), Depends(get_current_user)]. 3) Promote the API_KEY and JWT_SIGNING_KEY entries in validate_deployment_env from warnings to a hard SystemExit when NAME is not a dev value. | S (≈2h)
COR-01 | 2. Correctness | BLOCKER | ingest_jobs queue has no consumer in the only deployment path | start.sh; backend/app/worker/tasks.py; backend/app/services/ingest_job_runner.py | start.sh:169; tasks.py:51; ingest_job_runner.py:1119 | start.sh launches Celery with '--queues video_jobs' only. run_ingest_job_task is bound to queue='ingest_jobs' (tasks.py:51) and dispatched at ingest_job_runner.py:1119; the Celery beat auto-sync task also routes to INGEST_QUEUE (celery_app.py:67). The correct two-queue wiring exists ONLY in k8s/11-worker.yaml, Dockerfile.gpu-worker and docker-compose.gpu.yml — all confirmed unused. See the 'Queue Wiring' sheet for the full matrix. | The failure is completely silent. start_ingest_job_background falls back to a thread only if .delay() RAISES — but the broker accepts the message happily, so the fallback never triggers. The job is marked 'queued', the API returns 202, and the message sits in Redis forever with no timeout, no dead-letter and no alert. With ENABLE_AUTO_SYNC on, beat silently accumulates a message every night. | 1) Fix the deployed entrypoint and stop hardcoding: --queues "${WORKER_QUEUE:-video_jobs,ingest_jobs}". 2) CRITICAL PREREQUISITE: confirm what the external workflow actually uses as the worker command — if it does not use start.sh, fix it wherever that command is defined, and move that file into this repo. 3) Add a boot-time assertion comparing the consumed queue set against every queue= value registered on celery_app.tasks, warning loudly on any task whose queue nobody consumes. | S (≈1h) + unblocking
DEP-01 | 5. Config & Deploy | BLOCKER | Two divergent Dockerfiles; the likely-built one reintroduces the yt-dlp failure | Dockerfile; docker/Dockerfile | Dockerfile:1-25; docker/Dockerfile:1-41 | Neither Dockerfile is complete and they diverge on what matters. Root Dockerfile: no Node.js, HAS Whisper pre-download, no BuildKit cache, no non-root user. docker/Dockerfile: HAS Node 20, no Whisper pre-download, has BuildKit cache, no non-root user. docker/Dockerfile carries an explicit comment that without Node 'downloads silently fail as not available for every video'. | That comment describes the exact bug fixed in commit 6ed8f77. If the external workflow builds the repo-root Dockerfile (the conventional default), that fix is NOT in the deployed image and ingest returns zero videos with no error. If it builds docker/Dockerfile, every worker downloads the Whisper model at runtime instead, adding cold-start latency and a network dependency on first transcription. | 1) Determine which file gaiangroup/access/.github/workflows/python-ai4ia-nexusconnects.yaml@config builds — the highest-priority unknown in this audit, unanswerable from inside this repo. 2) Merge into ONE Dockerfile with Node 20 + Whisper pre-download + BuildKit cache + non-root USER; delete the other. 3) Add a build-time assertion so a regression fails the build, not production: RUN node --version && python -c "import faster_whisper". | M (≈4h)
TST-01 | 6. Testing | BLOCKER | Test suite does not collect; 73 unit tests fail | tests/unit/test_pipeline_base.py (+ suite-wide) | test_pipeline_base.py:13 | A bare pytest aborts during collection: "ImportError: cannot import name 'kill_running_stage' from 'app.pipeline.base'" — 889 items collected / 1 error / Interrupted. Excluding that module: 73 failed, 780 passed, 4 errors. Failures split into stale tests never updated after refactors (VIDEO_JOBS_DIR, get_supabase_client, _is_transient_connection_error, _render_one_segment) and non-hermetic tests reaching live Postgres, DNS, AWS and Ollama. Full breakdown on the 'Test Failures' sheet. | The suite provides zero signal, and 780 genuinely passing tests are hidden behind the noise. Combined with CI running no tests at all (DEP-02), this is why COR-01 and DEP-01 could go unnoticed. Every defect in this audit would have reached production unchallenged. | In order: 1) Repair or delete the stale modules so collection succeeds. 2) Add an autouse conftest fixture setting a dummy JWT_SIGNING_KEY — clears 14 failures immediately. 3) Mark infrastructure-dependent tests @pytest.mark.integration and default addopts to -m 'not integration'. 4) Wire the green suite into CI as a required gate. Verified: the _render_one_segment mismatch is test-side only; the production caller at segment_pipeline.py:800 matches. | L (≈1d)
SEC-02 | 1. Security | HIGH | Rate limiting is per-process and leaks memory | backend/app/core/rate_limit.py | 7-28 | TokenBucket holds _tokens and _last as plain in-process dicts with no eviction. With N API replicas the effective limit is N x the configured rate, and the dicts grow without bound keyed by user ID. | The login and OTP-resend limiters (auth_service.py:251, :136) are the brute-force defence on the auth surface. Horizontal scaling silently multiplies the allowance, and the unbounded dict is a slow leak on a long-lived API pod that an attacker can grow deliberately by varying the key. | Move to Redis, already a hard dependency — a Lua INCR+EXPIRE fixed-window is ~10 lines and shares state across replicas. If deferring, at minimum evict keys idle longer than _per inside allow(), and keep the in-process bucket only for non-security limiters. | M (≈4h)
SEC-03 | 1. Security | HIGH | OpenTelemetry API/SDK unpinned against instrumentation pinned at 0.44b0 | requirements.txt | 29-30 | opentelemetry-api and opentelemetry-sdk carry no version. Every instrumentation package is pinned to 0.44b0, whose declared constraint is only 'opentelemetry-api~=1.4' — satisfied by any 1.x. The local venv happens to hold 1.23.0; a clean build today resolves the newest 1.4x. | The 0.44b0 generation pairs with API 1.23. A fresh docker build — a rebuild, a cache miss, a new runner — can produce an image that fails at import inside setup_tracing(), which runs at main.py:24 BEFORE the app is constructed. The build succeeds and the container crash-loops. A latent, time-triggered outage. | Pin both to tested versions: opentelemetry-api==1.23.0 and opentelemetry-sdk==1.23.0. Also drop opentelemetry-exporter-jaeger-thrift==1.21.0 — a deprecated, removed-upstream exporter already version-skewed from the rest; .env points OTEL_EXPORTER_OTLP_ENDPOINT at an OTLP collector, so it is unused. | S (≈30m)
COR-02 | 2. Correctness | HIGH | LLM retry policy has no backpressure and fails in correlated bursts | backend/app/services/llm_service.py | 37-39, 56-87 | MAX_RETRIES=3 (3 attempts = 2 retries) with RETRY_SLEEP_SECONDS=4 fixed, no jitter, no exponential growth. A bare 'except Exception' retries everything including 4xx. A search for a semaphore, concurrency setting or queue throttle found NONE — no LLM concurrency limit exists anywhere in the codebase. | QUANTIFIED: total retry window is 4s + 4s = 8 seconds. Storyline/validation generations take tens of seconds, so when 16 slots contend for 10, the 6 overflow requests exhaust all three attempts inside 8s while the same 10 slots are still busy. The retries are CORRELATED, not independent — the p^3 intuition does not apply; effective failure probability stays approximately p. Under a synchronous burst of 16 against 10 that is roughly 6/16 = 37% of calls failing, in a clump. The un-jittered 4s also synchronises every retry into a thundering herd, and a 400 from a malformed payload burns 3 attempts and 8s of a worker slot. | Three changes by value: 1) SEMAPHORE — add llm_max_concurrency (default 8) to settings and wrap _post_with_retries in a module-level threading.BoundedSemaphore, so callers block instead of failing (latency instead of errors is the right trade for a batch pipeline). 2) BACKOFF+JITTER — sleep(min(60, 4 * 2**(attempt-1)) * random.uniform(0.5, 1.5)). 3) RETRY ONLY RETRYABLES — catch Timeout, ConnectionError and HTTPError with status in {429,500,502,503,504}; re-raise 4xx immediately. Add an llm_semaphore_wait_seconds histogram so saturation is visible before it becomes failure. | M (≈6h)
COR-03 | 2. Correctness | HIGH | Lazy media-registry rebuild scans local disk from an API pod that has none | backend/app/api/video_media.py; backend/app/services/media_registry.py | video_media.py:99-112; media_registry.py:67,76 | This is the live path still depending on ephemeral local disk — NOT LocalStorageService, which is correctly inert (ai4ia_storage_backend defaults to 's3' at settings.py:310 and .env confirms s3). _get_registry falls back to build_media_registry(job_id) for completed jobs, and that function decides what exists using Path(vp).exists() — a local filesystem check — while running on the API pod. The files were written on the WORKER pod, uploaded to S3, and their tmp dirs deleted at video_job_runner.py:481-483. | upload_job_outputs_to_s3 has a recovery path reconstructing entries from known S3 keys (storage_service.py:457-480), but the lazy rebuild does not call it. When the registry is missing — S3 upload failed, worker restarted mid-completion, registry written to a since-deleted emptyDir — the rebuild returns an empty or partial registry and the user gets a 404 on a video that exists in S3. This worsens with more than one API replica. | Make the lazy rebuild S3-aware: in S3 mode reconstruct from list_objects_v2(Prefix=f'jobs/{job_id}/') instead of local Path.exists(). Persist the registry to S3 as jobs/{job_id}/media_registry.json at completion so it is durable rather than rebuilt, and have _get_registry read that object first. | M (≈4h)
COR-04 | 2. Correctness | HIGH | acks_late + reject_on_worker_lost re-runs OOM-killed video jobs indefinitely | backend/app/worker/celery_app.py; backend/app/worker/tasks.py | celery_app.py:113-116; tasks.py:22-25 | Global config sets task_acks_late=True and task_reject_on_worker_lost=True. The tasks set max_retries=0, but that governs only explicit self.retry() — it does not stop broker-level redelivery when a worker dies. | A job heavy enough to OOM-kill the worker is redelivered on restart, OOMs again, and loops. The video pipeline is not idempotent, so each pass re-runs LLM calls and re-uploads to S3, burning GPU budget and leaving orphaned objects (DAT-03). Nothing bounds the cycle. | Track a delivery count in the job row and refuse execution past the second attempt: read job['delivery_attempts'], increment, and if > 2 call _fail_job(job_id, 'dispatch', 'poison_pill', ...) and return 'abandoned'. Emit a jobs_abandoned_total counter and alert on it — a worker-loss redelivery always warrants a human look. | S (≈3h)
ERR-01 | 3. Error handling | HIGH | Partial pipeline failure leaves no recovery path — only full re-run | backend/app/services/video_job_runner.py; backend/app/services/ingest_job_runner.py | video_job_runner.py:409-430; ingest_job_runner.py:802-847 | The stage loop breaks on the first failed stage and calls _fail_job. There is no resume-from-stage entry point — no API accepts 're-run job X starting at stage N'. The ingest runner does record per-video stage state via upsert_video_stage(vid, 'embed', 'failed', ...), which is good, but nothing ever reads that state back to resume. | A classification failure on video 47 of 50 discards 46 successful transcriptions on retry — hours of Whisper GPU time and LLM spend. The information needed to resume already exists in ingest_status; it is simply never consumed. | Add POST /api/ingest/jobs/{job_id}/resume reading per-video stage state and skipping any video whose stage is 'completed'. Give the video pipeline the same: persist stage_status and let run_video_job accept a start_at_stage argument, skipping stages whose outputs already exist in S3. Highest-value resilience work after the blockers. | L (≈2d)
OBS-01 | 4. Observability | HIGH | CONFIRMED: no worker health or readiness endpoint exists | backend/app/worker/ (no health surface) | n/a | Confirmed as flagged. grep -rn 'health' backend/app/worker/ returns nothing. The API's /api/health checks Redis, Supabase and Chroma and reports worker_mode — but that only reflects whether Redis is reachable from the API, not whether any worker is alive or consuming. | This is what makes COR-01 invisible. A worker consuming the wrong queue, a crash-looping worker, and a healthy worker are indistinguishable from outside. Combined with no queue-depth metric (OBS-02), jobs pile up indefinitely with every dashboard green. | Two pieces: 1) Add a liveness probe to the worker container using Celery's own ping — 'celery -A app.worker.celery_app inspect ping -d celery@$HOSTNAME', which docker-compose.gpu.yml:39 already demonstrates. 2) Extend /api/health to report the live worker set and its queues via celery_app.control.inspect().active_queues(), so a queue with no consumer becomes a visible degraded state rather than silence. | M (≈4h)
OBS-02 | 4. Observability | HIGH | No queue-depth metric — the one number that would expose the blocker | backend/app/core/metrics.py | n/a | Metrics cover LLM calls and latency, dependency health, rate-limit rejections, orphan reaps and auth events — genuinely good coverage. Queue depth is absent. | Queue depth is the single metric that makes 'enqueued but never consumed' visible. A gauge on ingest_jobs climbing monotonically from zero is unmistakable; without it the failure stays invisible until someone asks why ingestion stopped. | Add a gauge refreshed inside the existing _dependency_metrics_loop (main.py:128-148) — the loop already runs, this is a few lines inside it: for q in ('video_jobs','ingest_jobs'): celery_queue_depth.labels(queue=q).set(redis_client.llen(q)). | S (≈1h)
OBS-03 | 4. Observability | HIGH | Metrics are collected but nothing alerts — logs no one reads | (repo-wide: no alerting rules) | n/a | There are no alerting rules anywhere in the repo: no PrometheusRule, no Alertmanager config, no notification hook. Metrics are exposed at /metrics and traces exported to an OTel collector — both pull-only surfaces nobody is paged by. | Every silent failure in this audit — the unconsumed queue, yt-dlp returning zero videos, the redelivery loop — produces a clear metric signature and zero notifications. | Commit a PrometheusRule covering at minimum: celery_queue_depth > 0 for 15m on any queue; dependency_up == 0 for 5m; rate(jobs_failed_total[1h]) > 0.2 * rate(jobs_total[1h]); rate(llm_calls_total{outcome='failure'}[15m]) above a floor. Keep the rules in this repo so they are reviewed alongside the code emitting the metrics. | M (≈4h)
DEP-02 | 5. Config & Deploy | HIGH | CI runs no tests, no linting and no image scanning | .github/workflows/main.yaml | 1-35 | The workflow's only action is dispatching to an external reusable workflow per branch. There is no pytest, no ruff (despite it being a dev dependency with a populated .ruff_cache), no image vulnerability scan and no build verification. | This is why TST-01 went unnoticed: the suite has been failing to even import for some time and nothing surfaced it. There is no gate between a broken commit and production. | Add a 'test' job gating the deploy jobs via needs: — install .[dev], run 'ruff check' and 'pytest', and build the image. Deploy jobs then declare 'needs: test' so a red suite cannot ship. | M (≈4h)
DEP-03 | 5. Config & Deploy | HIGH | Stale infrastructure files misrepresent how the system is deployed | k8s/ (7 manifests); docker-compose.{api,gpu,infra,worker}.yml; DEPLOYMENT.md | k8s/11-worker.yaml:25-42; docker-compose.worker.yml:4; DEPLOYMENT.md:147 | Confirmed with the user: none of these deploy anything. They are the most detailed operational documentation in the repo and describe a system that does not exist — image tag v2.9-gpu, GPU node selectors, resource requests/limits, emptyDir volumes and a two-queue worker command. | This is what made COR-01 so easy to miss: the correct queue configuration sits right there in k8s/11-worker.yaml looking authoritative. Any reviewer would conclude the queues are wired correctly. Stale infrastructure-as-code is worse than none — it reads as ground truth. | Delete k8s/ and the four compose files, or move them to examples/local-dev/ behind a header stating they are not the deployment path. Rewrite DEPLOYMENT.md to describe the actual path: which workflow, which Dockerfile, where the worker command is defined, where secrets come from. If the real manifests live in gaiangroup/access, say so and link it — an auditor must be able to find the deployed worker command. | S (≈2h)
TST-02 | 6. Testing | HIGH | Critical paths with zero test coverage | tests/ (47 unit modules present) | n/a | Against the 47 unit modules present, these paths have no test: queue routing (nothing asserts every queue= declared on a task is consumed by the deployed worker command); LLM retry/backoff (test_llm_service.py exists but omits retry exhaustion, partial failure and concurrency); S3 upload/download round-trip (test_storage_service.py covers LocalStorageService only — S3StorageService has no moto-backed test); job state transitions (queued/running/failed/orphan-reap lifecycle, and the redelivery path in COR-04); Chroma/Postgres consistency (the divergence in DAT-01). | A four-line queue-routing assertion would have caught the top blocker. The S3 gap means the primary storage backend in production is exercised by nothing. | Start with the queue-routing assertion and a moto-backed S3 round-trip — both cheap, and they cover the two highest-impact blind spots. Then add job-state-transition tests including the poison-pill path. | L (≈2d)
DAT-01 | 7. Data integrity | HIGH | Chroma/Postgres divergence on partial embedding failure is silent and unrecoverable | scripts/import_embeddings_to_chroma.py | 207-219 | Three defects in one loop. NO ATOMICITY: collection.add(...) is unguarded, so a failure at batch i aborts the script with batches 0..i-1 already committed to Chroma — no rollback, no resume marker. SILENT DIVERGENCE: a Postgres failure is caught and printed as '[warn]' while the script continues, so Chroma holds the vector and Postgres has no row. BROKEN RETRY: it uses collection.add, not upsert, so re-running after a partial failure raises on already-present IDs (reembed_fragments.py:315 correctly uses upsert; this path was not updated). | The quietest corruption mode in the system. Semantic search returns fragment IDs that resolve to nothing, the process exits 0, search degrades gradually as divergence accumulates, and the only evidence is a [warn] line in stdout that nothing aggregates. | 1) Write Postgres FIRST, then Chroma, so a failure leaves an un-embedded row (recoverable) rather than an unreferenced vector (invisible). 2) Switch add to upsert for idempotent retries. 3) Make the Postgres failure fatal rather than a warning. 4) Add a reconciliation command comparing Chroma IDs against Postgres fragment IDs and reporting drift in both directions — scripts/reconcile_archive_stores.py may be the right home. | M (≈6h)
DAT-02 | 7. Data integrity | HIGH | Migrations are unordered, untracked and not reversible | db/migrations/; backend/app/db/schema.py | schema.py:196-205 | No migration runner, no schema_migrations table, no ordering enforcement — files are applied by hand. Numbering gaps: db/migrations/ holds 0003, 0004, 0005 only, with db/init/001_schema.sql separate. A 0005 COLLISION: 0005_otp_email_change_purposes.sql exists on disk, but session_service.py:1 and session_repository.py:4 both reference db/migrations/0005_user_sessions.sql, which does not exist. No '-- Down' sections anywhere. Separately, ensure_pipeline_schema() runs DDL on every API startup. | Nobody can answer 'what schema is production on?' from the repo. 0005_user_sessions.sql being referenced but absent means a fresh environment cannot be built from this repository at all. Rollback means hand-writing inverse DDL under incident pressure. And with multiple replicas booting together, concurrent CREATE INDEX can deadlock in Postgres. | 1) URGENT: locate or reconstruct the missing 0005_user_sessions.sql and renumber it. 2) Adopt a real runner (Alembic) with a schema_migrations ledger. 3) Renumber existing files into one contiguous sequence and add '-- Down' sections. 4) Move ensure_pipeline_schema out of startup into an init container or explicit job so it runs once per deploy, not once per replica. | L (≈2d)
SEC-04 | 1. Security | MEDIUM | No request body size limit anywhere in the stack | backend/app/main.py (middleware chain) | 207 | No middleware or reverse-proxy config in the repo caps request body size. The only size check is translation_max_body_bytes on RESPONSES (middleware/translation.py:170). | POST /api/video-jobs and /archive/semantic-search take JSON parsed fully into memory before validation. A single large body can OOM an API pod; k8s restarts it and drops every in-flight SSE stream. | Add a middleware rejecting Content-Length over ~1 MB with 413 before the body is read, and confirm the ingress in the external workflow sets proxy-body-size. | S (≈1h)
SEC-05 | 1. Security | MEDIUM | /metrics is unauthenticated and exposes internal topology | backend/app/main.py | 186-188 | The Prometheus endpoint is exposed with no auth, deliberately ('unauthenticated, same as /api/health'). | Unlike /api/health, the metrics payload enumerates every route path, request volumes, LLM host labels (llm_calls_total{host=...}) and job success/failure counts. If the ingress exposes the API publicly this is a free internal map and a business-volume leak. | Either bind metrics to a second port not routed by the ingress (cleaner in k8s), or gate it on require_api_key and set the scrape config's bearer token. | S (≈2h)
SEC-06 | 1. Security | MEDIUM | .env is tracked in git while .env.example is ignored — exactly backwards | .gitignore; .env | .gitignore:18 | .gitignore line 18 ignores .env.example, and the real-credential lines (.env.* / !.env.example) are commented out. git ls-files confirms .env is tracked and present in HEAD. | The file that should be committed is ignored; the file that should never be committed is tracked. Today's .env is scrubbed so this is not a live exposure — it is a loaded gun. The next person who adds AWS_SECRET_ACCESS_KEY locally commits it with no warning, which is plausibly how the original incident occurred. | git rm --cached .env, then correct the ignore rules to: .env / .env.* / !.env.example. Add a gitleaks or detect-secrets pre-commit hook plus a CI scan step so this is enforced rather than remembered. | S (≈1h)
SEC-07 | 1. Security | MEDIUM | Containers run as root; no S3/IAM policy defined in the repo | Dockerfile; docker/Dockerfile | Dockerfile:1-25; docker/Dockerfile:1-41 | Neither Dockerfile declares a USER, so both API and worker run as UID 0. Separately there is no IAM policy, bucket policy or lifecycle configuration anywhere in the repo — S3 scope could not be audited because it is not expressed as code. | Root plus a pipeline shelling out to ffmpeg and yt-dlp on untrusted remote input is a poor combination. S3 permissions not visible in review are permissions nobody reviews — the app only ever needs GetObject/PutObject/DeleteObject/ListBucket on ai4ia-data/*. | Add to both Dockerfiles before CMD: RUN useradd -m -u 10001 app && chown -R app:app /app ; USER app. Commit the intended bucket policy and IAM role as Terraform or a README block so drift is reviewable, and set a k8s securityContext with runAsNonRoot: true in whatever the external workflow templates. | M (≈3h)
SEC-08 | 1. Security | MEDIUM | Prior audit's CRITICAL-1 (secrets in git history) does not reproduce — verify rotation happened | docs/AI4IA_Production_Readiness_Audit.xlsx (Critical Findings, rank 1); .env.example history | n/a | The previous audit (dated 2026-08-24) lists 'Live production secrets committed to git history' as CRITICAL rank 1, citing .env.example. Re-scanning every commit touching .env.example (4043cfd, 5fdf950, 1e0c038) shows only placeholders: AWS_SECRET_ACCESS_KEY=changeme..., SUPABASE_SERVICE_KEY=changeme..., JWT_SIGNING_KEY=changeme..., MAIL_SMTP_PASSWORD=changeme..., DATABASE_URL=postgresql://user:pass@host:5432/ai4ia # [secret]. No JWT-shaped tokens and no AKIA identifiers anywhere in git log --all -p. | Either the finding was remediated between audits, or it was a false positive. This matters because the two remediations are different: scrubbing history does NOT rotate credentials. If secrets were genuinely exposed and only the history was rewritten, the live credentials are still compromised. | Confirm with whoever actioned the previous audit which happened. If any credential was ever committed, rotate it now regardless of current history state: Supabase service_role, AWS access keys, SMTP password and JWT signing key. Record the rotation date so the next audit does not have to re-litigate this. | S (verification)
COR-05 | 2. Correctness | MEDIUM | Hardcoded worker_concurrency=1 contradicts every other concurrency declaration | backend/app/worker/celery_app.py; backend/app/core/settings.py | celery_app.py:110; settings.py:291 | Celery config hardcodes worker_concurrency=1 with the comment 'At most 1 video pipeline per worker process (heavy CPU/GPU work)'. Meanwhile .env sets WORKER_CONCURRENCY=6, settings.worker_concurrency defaults to 1, and start.sh passes --concurrency "$CONCURRENCY" — and the CLI flag wins over the config value. | The stated safety invariant is not enforced anywhere. Whatever $CONCURRENCY resolves to at runtime silently overrides it, so N concurrent video pipelines — each spawning ThreadPoolExecutor(max_workers=8) at stage_09_export.py:141 — can share one pod's memory. That is the OOM feeding the COR-04 redelivery loop. | Delete the hardcoded line and drive it from settings (worker_concurrency=settings.worker_concurrency) so there is exactly one source of truth, then set that value deliberately against the pod memory limit and the 8-thread render fan-out. | S (≈1h)
COR-06 | 2. Correctness | MEDIUM | embed_celery_worker is half-wired — declared, never implemented | backend/app/core/settings.py; tests/unit/test_settings.py | settings.py:290; test_settings.py:53 | Confirmed as asked. The flag exists as a setting and has a test asserting its default is False. Nothing reads it. There is no code path that would embed a Celery worker in the API process. settings.worker_queue (settings.py:292) is equally inert — never read, yet actively set in .env where it does nothing. | A setting with a test but no implementation reads as a supported feature. Someone will set it true expecting in-process workers, observe no error, and conclude jobs are being consumed — the same silent-success failure as COR-01. | Delete the setting and its test; the thread-fallback path in start_ingest_job_background already covers the no-Redis case this was presumably meant to serve. Remove worker_queue at the same time, OR wire it into start.sh per the COR-01 fix — either is acceptable, but it must not stay inert. | S (≈1h)
COR-07 | 2. Correctness | MEDIUM | Completion event emitted from a failed job load reports video_url: None | backend/app/services/video_job_runner.py | 467-469, 486-494 | Residual defect found while verifying the load_job ordering fix. If the post-completion load_job at line 467 fails, 'job' stays None, a warning is logged, and line 488 still emits a 'completed' event built from that None — yielding video_url: None. | The client sees a successful job with no video link, for a video that rendered and uploaded correctly. Indistinguishable from a genuine render failure by anyone reading the event stream. | Set the job status to 'degraded' or re-raise, rather than emitting a completion event built from a failed load. At minimum, derive the URL from the media registry (which does its own load) instead of the possibly-None local variable. | S (≈1h)
ERR-02 | 3. Error handling | MEDIUM | FFmpeg subprocesses set no timeout of their own | backend/app/pipeline/export_gen/ffmpeg_utils.py; export_gen/segment_pipeline.py | ffmpeg_utils.py:15,30; segment_pipeline.py:661 | Three subprocess.run calls invoke FFmpeg with no timeout kwarg. run_cmd at ffmpeg_utils.py:15 is the main render helper. | NOT a blocker, because these run inside stage subprocesses launched by base.run_script, which applies _STAGE_TIMEOUTS (base.py:52-60: 900s for 09_export) and kills the whole process group via os.setsid + killpg. A hung FFmpeg is bounded at the stage level. The residual risk is attribution: the job fails as 'stage 09 timed out' with no indication which of the 8 parallel renders hung, and the 900s budget is shared across the whole fan-out. | Pass a per-call timeout to run_cmd (default ~300s) and raise a distinct FFmpegTimeout naming the segment index and input file. Cheap, and turns an opaque stage timeout into an actionable log line. | S (≈2h)
ERR-03 | 3. Error handling | MEDIUM | No dead-letter queue or failure visibility beyond log lines | backend/app/worker/celery_app.py | 96-123 | No task_annotations, no dead-letter routing, no on_failure handler. A task that raises logs an exception and updates job status; nothing aggregates failures. | With result_expires=86400, evidence of a failure is gone after 24h. There is no queue a human can inspect to answer 'what failed overnight and why'. | Add a Celery task_failure signal handler writing to the existing job_events table with a 'terminal_failure' type, and surface those through the provenance feed. The storage and admin-gated endpoint already exist — this is wiring, not new infrastructure. | M (≈3h)
DEP-04 | 5. Config & Deploy | MEDIUM | Workflow branch logic has a dead job and an unhandled branch | .github/workflows/main.yaml | 2-4, 12-13, 30-31 | Three defects: prod_job fires on refs/heads/prod but 'prod' is not in on.push.branches, so the job can never run; 'nexusconnects' IS a trigger branch but matches no deploy job, falling through to unauthorized_branch_job; and the guard condition tests 'release' twice while never testing 'nexusconnects'. | Someone pushing to 'prod' expecting a production deploy gets total silence — no job, no error. A dangerous shape of failure for a deploy pipeline. | Derive the branch list and job conditions from one source; delete prod_job or add 'prod' to the trigger list; give nexusconnects an explicit job. Separately confirm that 'release' calling python-mobius-graph-operations-release-config.yaml — a different workflow from every other branch, named for a different service — is intentional and not copy-paste. You are releasing from this branch. | S (≈2h)
DEP-05 | 5. Config & Deploy | MEDIUM | Resource limits for Whisper and the GPU variant are not reviewable | k8s/11-worker.yaml (stale — not deployed) | 40-42 | The only limits in the repo are in the stale manifest: requests cpu 2 / mem 4Gi; limits cpu 6 / mem 12Gi / 1 GPU / 60Gi ephemeral. Since that file does not deploy, the ACTUAL limits are not visible in this repo and could not be audited. | Two specific risks to verify wherever limits really live. Whisper 'small' at int8 needs roughly 2GB per concurrent transcription, so a 12Gi limit tolerates few parallel jobs — and with $CONCURRENCY possibly 6 (per .env) against the 8-thread render fan-out, 12Gi is plausibly exceeded. That is the OOM feeding COR-04. Second, emptyDir for /app/data/jobs means job state is lost on pod restart — the failure the S3 migration was meant to eliminate. | Get the real manifests into review. Then set memory limits from measured peak RSS under $CONCURRENCY parallel jobs rather than inherited values, and confirm no pipeline output depends on an emptyDir surviving a restart. | M (blocked on access)
TST-03 | 6. Testing | MEDIUM | Testing the ordering fix under load needs staging — but the useful test does not | tests/unit/test_video_job_runner.py; k6/ | n/a | Answering the question directly: partly. The concurrency behaviour needs a staging run, and k6/ holds an existing harness (k6.js, test_whisper_gpu.py, reports at 10/20/50 VU) that could be pointed at it. But the fix's actual logic needs no load at all. | As traced in the ordering verification, the sequencing was never the coupling — build_media_registry does its own load_job. The real behaviour to pin is that each step is independently isolated. | Write a unit test now: mock load_job to raise and assert build_media_registry and upload_job_outputs_to_s3 still execute — roughly 20 lines, no infrastructure, and it pins the regression 6ed8f77 fixed. Reserve staging for the genuinely concurrent questions: worker memory under $CONCURRENCY parallel jobs, and the LLM saturation in COR-02 (also where the ~37% burst estimate would be empirically confirmed). | S (≈2h)
DAT-03 | 7. Data integrity | MEDIUM | Failed jobs leave orphaned S3 objects; no lifecycle policy exists | backend/app/services/video_job_runner.py | 200-205, 426, 509 | Answering the question directly: accumulating. _cleanup_job_tmp_dirs — the only cleanup on the failure path — removes LOCAL /tmp/ai4ia_pipeline/* directories only. Nothing deletes S3 objects. A job failing at stage 10 or 11, after stages 08/09 uploaded assets, leaves those objects orphaned permanently. No bucket lifecycle rule exists in the repo. | Unbounded storage growth proportional to the failure rate, and every orphan is a video asset with no owning job row — so it never appears in any UI and is only findable by bucket diff. | Two layers: 1) In _fail_job, delete jobs/{job_id}/ via list_objects_v2 + delete_objects — S3StorageService.delete_object already exists at storage_service.py:368. 2) As a backstop, add an S3 lifecycle rule expiring objects under a tmp/ prefix after 7 days, committed as code alongside the IAM policy from SEC-07. | M (≈3h)
SEC-09 | 1. Security | LOW | yt-dlp unpinned — correct, but make it deliberate | requirements.txt | 43 | yt-dlp floats. This is defensible: a pinned yt-dlp goes stale within weeks as YouTube changes. | It means image builds are not reproducible and a bad upstream release reaches production with no gate. | Keep it floating but add a comment stating why, and pin a lower bound (yt-dlp>=2025.1.1). Record the resolved version in the image (pip freeze > /app/BUILD_VERSIONS.txt) so a failing download can be traced to a version. | S (≈30m)
SEC-10 | 1. Security | LOW | YouTube URL validation not enforced at the API boundary | backend/app/api/ingest.py; backend/app/schemas/pipeline.py | n/a | Ingest routes are admin-gated (_admin_dep), which is the main control. Video identifiers still flow into subprocess argv for yt-dlp without a format assertion at the schema layer. | Low severity because the surface is admin-only and calls use argv lists, not a shell — so this is NOT command injection. It is an input-hygiene gap that would matter the moment ingest is delegated to a non-admin role. | Add a Pydantic validator constraining video IDs to ^[A-Za-z0-9_-]{11}$ and channel URLs to an allowlist of YouTube hosts, so validation lives at the boundary rather than depending on the role gate. | S (≈1h)
COR-08 | 2. Correctness | LOW | CORRECTION: the named dead-code files do not exist | backend/app/api/; backend/app/services/ | n/a | Checked as asked. storylines.py, assets.py, exports.py and job_service.py do NOT exist anywhere in the tree — they were removed in an earlier refactor. All 12 routers in backend/app/api/ are imported and mounted in main.py:26-37. There is no legacy router cleanup remaining. | No production risk. Recorded so the next audit does not re-investigate, and so the remediation backlog is not padded with work that is already done. | No action on these files. The genuine dead config is settings.embed_celery_worker and settings.worker_queue — tracked separately as COR-06. LocalStorageService is genuinely reachable via AI4IA_STORAGE_BACKEND=local; keep it, it is the test path. | None
DEP-06 | 5. Config & Deploy | LOW | Hardcoded tuning values that should be configuration | stage_09_export.py; llm_service.py; base.py; celery_app.py | stage_09_export.py:141,279; llm_service.py:37-39; base.py:52-60; celery_app.py:110 | Endpoints, bucket names and model names are properly externalised through settings.py — that part is clean. What remains hardcoded is concurrency and tuning: ThreadPoolExecutor(max_workers=8) (the main memory driver during render), max_workers=4, REQUEST_TIMEOUT_SECONDS/MAX_RETRIES/RETRY_SLEEP_SECONDS, _STAGE_TIMEOUTS (notably 900s for 09_export), and worker_concurrency=1. | These are exactly the knobs needed during a production incident, and each currently requires a rebuild to change. | Move them to settings.py with the current values as defaults — behaviour-preserving, and it makes tuning a config change rather than a release. | M (≈3h)

## Remediation Plan
Remediation Plan
Sequenced by dependency, not just severity. P0 items gate the release.
Priority | ID | Finding | Owner area | Effort | Depends on | Verification method | Done?
P0 | DEP-01 | Determine which Dockerfile the external workflow builds; merge to one | DevOps | M (≈4h) | — | Inspect the reusable workflow in gaiangroup/access. Then: docker run <image> node --version && python -c 'import faster_whisper' both succeed.
P0 | COR-01 | Wire the deployed worker to consume ingest_jobs | DevOps + Backend | S (≈1h) | DEP-01 | Trigger an ingest job; assert it reaches 'running' within 60s. Then 'celery inspect active_queues' lists both queues.
P0 | TST-01 | Repair test collection and the 73 failing unit tests | Backend | L (≈1d) | — | 'pytest' exits 0 with no collection errors and no failures outside @pytest.mark.integration.
P0 | DEP-02 | Add a CI test gate ahead of the deploy jobs | DevOps | M (≈4h) | TST-01 | Push a deliberately failing test to a branch; confirm the deploy job does not run.
P0 | SEC-01 | Fail closed on missing API_KEY; add get_current_user to archive/dashboard | Backend | S (≈2h) | — | Unset API_KEY → app refuses to serve (503). Request to /archive/videos without a bearer token → 401.
P1 | SEC-03 | Pin opentelemetry-api and -sdk to 1.23.0; drop the Jaeger exporter | Backend | S (≈30m) | — | Build the image from a clean cache (--no-cache); container starts and /metrics responds.
P1 | COR-02 | Add an LLM semaphore, jittered exponential backoff, retryable-only errors | Backend | M (≈6h) | — | Staging load test at 16 concurrent jobs; LLM failure rate under 2% and llm_semaphore_wait_seconds is populated.
P1 | DAT-02 | Recover the missing 0005_user_sessions.sql; adopt a migration runner | Backend + DBA | L (≈2d) | — | A fresh database can be built from db/ alone and the app boots against it.
P1 | DAT-01 | Reorder Chroma/Postgres writes; switch add→upsert; make PG failure fatal | Backend | M (≈6h) | — | Kill the import mid-batch, re-run, and confirm it completes with no duplicate-ID error and zero ID drift.
P1 | COR-04 | Bound worker-loss redelivery with a delivery-attempt counter | Backend | S (≈3h) | — | SIGKILL a worker mid-job; confirm the job is abandoned on the third delivery and jobs_abandoned_total increments.
P1 | OBS-01 | Add a worker liveness probe and report worker queues in /api/health | DevOps + Backend | M (≈4h) | COR-01 | Stop the worker; /api/health reports degraded within 60s.
P1 | OBS-02 | Add a celery_queue_depth gauge to the dependency metrics loop | Backend | S (≈1h) | — | Enqueue with no worker running; the gauge climbs and is visible at /metrics.
P1 | OBS-03 | Commit PrometheusRule alerting for queue depth, deps, failure rate | DevOps | M (≈4h) | OBS-02 | Force each alert condition in staging and confirm it fires to the real notification channel.
P1 | COR-03 | Make the lazy media-registry rebuild S3-aware; persist registry to S3 | Backend | M (≈4h) | — | Delete a local registry, request the asset from a second API replica, and receive 200.
P1 | DEP-03 | Delete or quarantine k8s/ and docker-compose; rewrite DEPLOYMENT.md | DevOps | S (≈2h) | DEP-01 | A reviewer can identify the deployed worker command from the repo in under five minutes.
P1 | SEC-08 | Confirm whether the prior audit's secret exposure was rotated or a false positive | Security | S | — | Written confirmation of rotation date, or confirmation the finding was a false positive.
P2 | ERR-01 | Add resume-from-stage for ingest and video pipelines | Backend | L (≈2d) | DAT-02 | Fail a job at stage 10, resume it, and confirm stages 07-09 are skipped.
P2 | SEC-02 | Move rate limiting to Redis | Backend | M (≈4h) | — | Two API replicas share one limit: the Nth+1 request is rejected regardless of which replica serves it.
P2 | TST-02 | Add queue-routing, moto-backed S3, and job-state-transition tests | Backend | L (≈2d) | TST-01 | A deliberate single-queue regression fails the new routing test.
P2 | COR-05 | Remove the hardcoded worker_concurrency; drive it from settings | Backend | S (≈1h) | — | WORKER_CONCURRENCY=2 is reflected in 'celery inspect stats'.
P2 | SEC-07 | Add non-root USER to the Dockerfile; commit the IAM and bucket policy | DevOps | M (≈3h) | DEP-01 | 'docker run <image> id -u' returns 10001; the IAM policy is in review.
P2 | DAT-03 | Delete S3 objects on job failure; add a lifecycle rule | Backend + DevOps | M (≈3h) | — | Fail a job after stage 09 and confirm jobs/{job_id}/ is empty afterwards.
P2 | SEC-04 | Add a request body size limit | Backend | S (≈1h) | — | A 5 MB POST body is rejected with 413.
P2 | SEC-05 | Move /metrics off the public ingress or gate it | DevOps | S (≈2h) | — | /metrics is unreachable from outside the cluster.
P2 | SEC-06 | Untrack .env; fix .gitignore; add a secret-scanning hook | Backend | S (≈1h) | — | A commit containing a test secret is blocked by the pre-commit hook.
P3 | COR-06 | Delete embed_celery_worker and worker_queue, or wire worker_queue up | Backend | S (≈1h) | COR-01 | No inert settings remain: every field in settings.py has a reader.
P3 | COR-07 | Stop emitting a completion event from a failed job load | Backend | S (≈1h) | — | Mock load_job to raise; assert no 'completed' event carrying video_url: None is emitted.
P3 | ERR-02 | Add per-call FFmpeg timeouts naming the segment | Backend | S (≈2h) | — | A stalled render fails with a message identifying the segment index.
P3 | ERR-03 | Add a task_failure handler writing terminal failures to job_events | Backend | M (≈3h) | — | A failed task appears in the provenance feed.
P3 | DEP-04 | Fix the workflow's dead prod_job and unhandled nexusconnects branch | DevOps | S (≈2h) | — | Every branch in on.push.branches maps to exactly one deploy job.
P3 | DEP-05 | Get the real resource limits into review and size them from measurement | DevOps | M | DEP-01 | Peak RSS measured under $CONCURRENCY parallel jobs sits below the memory limit.
P3 | DEP-06 | Move hardcoded tuning values into settings.py | Backend | M (≈3h) | — | Render fan-out and stage timeouts are changeable without a rebuild.
P3 | TST-03 | Unit-test the load_job isolation behaviour | Backend | S (≈2h) | TST-01 | Mock load_job to raise; assert build_media_registry and the S3 upload still run.
P3 | SEC-09 | Add a yt-dlp lower bound and record resolved versions in the image | Backend | S (≈30m) | — | /app/BUILD_VERSIONS.txt exists in the image.
P3 | SEC-10 | Validate YouTube IDs and channel hosts at the schema boundary | Backend | S (≈1h) | — | A malformed video ID is rejected with 422.
P3 | COR-08 | No action — recorded correction only | — | None | — | None required; logged so the finding is not re-investigated.

## Queue Wiring
Celery Queue Wiring — End-to-End Matrix
Evidence for COR-01. Every declaration of a worker command in the repository, and whether it deploys.
Location | Queues consumed | Concurrency | Deployed? | Assessment
start.sh:169 | video_jobs | $CONCURRENCY | YES — entrypoint | THE BUG. ingest_jobs is never consumed.
k8s/11-worker.yaml:31 | video_jobs,ingest_jobs | 4 | No — stale | Correct, but does not deploy. Misleads reviewers.
Dockerfile.gpu-worker:52 | video_jobs,ingest_jobs | 2 | No — unused image | Correct, but does not deploy.
docker-compose.gpu.yml:25 | video_jobs,ingest_jobs | 2 | No — stale | Correct, but does not deploy.
docker-compose.worker.yml:4 | video_jobs | 2 | No — stale | Also wrong, and also does not deploy.
DEPLOYMENT.md:147 | video_jobs | 2 | No — stale doc | Documents the wrong command as if authoritative.
PRODUCERS — who enqueues to ingest_jobs
Location | Task / trigger | Target queue | Reached by a worker? | Consequence
backend/app/worker/tasks.py:51 | run_ingest_job_task | ingest_jobs | NO | Task definition binds the queue nobody consumes.
backend/app/services/ingest_job_runner.py:1119 | .delay(job_id) | ingest_jobs | NO | Broker accepts it, so the thread fallback never fires. Job sits at 'queued' forever.
backend/app/worker/celery_app.py:67 | beat: auto_sync_channel | ingest_jobs | NO | With ENABLE_AUTO_SYNC on, beat silently accumulates one dead message per night.
FIX — 1) start.sh:169 becomes --queues "${WORKER_QUEUE:-video_jobs,ingest_jobs}". 2) PREREQUISITE: confirm the external workflow actually uses start.sh; if not, fix the command wherever it is defined and move that file into this repo. 3) Add a boot-time assertion comparing the consumed queue set against every queue= registered on celery_app.tasks, warning loudly on any task whose queue nobody consumes — this turns the whole class of bug from silent to obvious.

## Dockerfile Diff
Dockerfile Comparison
Evidence for DEP-01. Neither file is complete, and they diverge on what matters.
Capability | /Dockerfile | /docker/Dockerfile | Consequence if this one is built
Node.js 20 (yt-dlp JS challenge) | MISSING | Present | Root: every YouTube download silently fails as 'not available'. This is the bug fixed in 6ed8f77.
Whisper model pre-baked | Present | MISSING | docker/: workers download the model at runtime — cold-start latency and a network dependency on first transcription.
BuildKit pip cache mount | No | Yes | Root: slower builds only. No runtime impact.
Non-root USER | No | No | Both: API and worker run as UID 0 alongside ffmpeg/yt-dlp on remote input. See SEC-07.
PYTHONUNBUFFERED / DONTWRITEBYTECODE | No | Yes | Root: logs may buffer, degrading observability in k8s.
EXPOSE 8000 | No | Yes | Documentation only. No runtime impact.
FIX — Merge into ONE Dockerfile carrying Node 20, the Whisper pre-download, the BuildKit cache mount and a non-root USER; delete the other. Add a build-time assertion so a regression fails the build rather than production: RUN node --version && python -c "import faster_whisper"

## Test Failures
Test Suite Analysis
Evidence for TST-01. Run: pytest -q (venv, 2026-09-15). Collection aborts; excluding test_pipeline_base.py gives 73 failed / 780 passed / 4 errors.
Failure cause | Count | Class | Remedy
ImportError: kill_running_stage (aborts ALL collection) | 1 | Stale test | Symbol removed from app.pipeline.base. Repair or delete tests/unit/test_pipeline_base.py — until then a bare pytest collects nothing.
Live Postgres on localhost — password authentication failed | 24 | Not hermetic | Mark @pytest.mark.integration and default addopts to -m 'not integration'.
Ollama /api/embed — not enough values to unpack | 24 | Not hermetic | Mock the embedding client; these reach a real Ollama host.
video_job_runner.VIDEO_JOBS_DIR no longer exists | 22 | Stale test | Attribute removed in the S3 migration. Update the tests to patch the storage service instead.
HMAC key must not be empty | 14 | Missing fixture | Add an autouse conftest fixture setting a dummy JWT_SIGNING_KEY. Clears all 14 immediately — cheapest win in the suite.
job_repository._is_transient_connection_error renamed | 10 | Stale test | Update the patch target to the current symbol name.
AWS credentials / DNS resolution failures | 13 | Not hermetic | Replace with moto-backed fixtures; this also closes the S3 coverage gap in TST-02.
job_repository.get_supabase_client removed | 4 | Stale test | Removed in the Postgres migration. Update or delete.
_render_one_segment() takes 3 args but 4 were given | 4 | Stale test | VERIFIED test-side only — the production caller at segment_pipeline.py:800 matches the signature. No production bug.
Roughly half are refactor drift; the other half cannot pass in CI at all. 780 genuinely passing tests are hidden behind the noise.

## Verified Clear
Verified Clear — Items Checked That Are Not Defects
Recorded so the next audit does not re-investigate, and so two incorrect premises are corrected on the record.
Item checked | Method | Result
No exposed Supabase service_role key or AWS credentials | git log --all -p scanned for JWT-shaped tokens (eyJ...), AKIA identifiers, and assignments to *_SERVICE_KEY / AWS_SECRET_ACCESS_KEY / MAIL_SMTP_PASSWORD / DATABASE_URL across every commit touching .env and .env.example. | CLEAN — every hit is a placeholder ('changeme...', '# [secret]', 'postgresql://user:pass@host'). Commit d3b342c ('removing keys') removed an already-empty API_KEY=. The regression you asked about has NOT recurred. See SEC-08 for the discrepancy with the prior audit.
load_job / build_media_registry ordering fix | Traced video_job_runner.py:463-496 and every caller of build_media_registry (video_media.py:112, storage_service.py:457, 4 test call sites). | CORRECT, and no other call site depends on the old order — but not for the assumed reason. build_media_registry performs its OWN load_job at media_registry.py:61, so it never consumed the runner's variable; the coupling was never real. The genuine fix was isolating each step in its own try/except so one failure no longer skips the S3 upload. Residual defect logged as COR-07.
HTTP timeouts on all external calls (S3, Supabase, vLLM, Ollama) | AST pass over backend/app for requests/httpx calls missing a timeout kwarg (an initial line-scoped grep gave false positives on multi-line calls and was discarded). | CLEAN — zero results. LLM path 120s, Ollama warm-up 600s, embedding cache 30s, Chroma health check 4s. The concern that a hung LLM request blocks a worker slot indefinitely does NOT apply at the HTTP layer; the real exposure is the retry arithmetic in COR-02. Subprocess gaps tracked as ERR-02.
End-to-end job tracing from job ID | Reviewed main.py:40-71 logging setup, video_job_runner.py:410 span creation, and _job_logger usage. | WORKING — _PipelineLogFilter injects job_id/stage/otelTraceID/otelSpanID onto every record, JSON formatting activates on LOG_FORMAT=json, and stage execution is wrapped in a span carrying job_id. A failed job can be traced end to end by job ID. Strongest area of the codebase.
LocalStorageService not in the live path | Checked ai4ia_storage_backend default (settings.py:310 = 's3'), .env value, get_storage_service() dispatch (storage_service.py:506-516) and all references. | CONFIRMED INERT via config — but see COR-03. The live local-disk dependency is not LocalStorageService; it is build_media_registry's Path(vp).exists() check running on an API pod that holds no job files.